## WorkOrderSearch (83)
Work Order | Date Kitted | Priority | Charge To Name | Description | Man Hrs | Requested by
17004298 | 2017-05-20 | 2 | Bread Basket Loader L1PF4 | Change all o-rings on the roller bed. | 5 | Robert
17004552 | 2017-02-22 | 2 | Bread Bagger L2B2 | L2B2 replace blockade piston part # ASCYLD159. 0, instock needs to be ordered PART REQUEST SUBMITTED 22 FEBRUARY 2017 | 1.5 | Robert
17005157 | 2017-02-25 | 1 | Bread Splitter / Applicator L2WS | Vacuum Motor is bad, order and replace. | 2.5 | Robert
17006085 | 2017-03-04 | 2 | Bread Dough Mixer M11MIX | Replace air conditioner on electrical panel. New one located in receiving. (See Shawn) | 3 | Robert
17006086 | 2017-03-04 | 2 | Bread Wrapping Electrical Panel EP-EB | Electrical panel is over 100. Check filters and air conditioning. Clean coils and all parts of the air conditioning unit. | 2 | Robert
17008452 | 2017-03-19 | 3 | Bread Wrapping Electrical Panel Full Basket Return Conveyors | Check and repair AC unit at L1 Tray feed to stackers FB-1 panel | 2 | Robert
17008598 | 2017-03-20 | S | BREAD LINES 1 AND 2 | new racks in wrapping have some sharp edges. Please review and sand down accordingly. | 2 | Robert
17008857 | 2017-03-22 | 2 | Bread Twin Pack Bagger L2TPB3 | *****Determine the parts needed to replace these conveyors with Intralox conveyors (one has already been done). Write a parts list for the other two twin pack baggers and provide this list to the maintenance planner.***** We need to disassemble this conveyor, replace the sprockets and belt if possible.Lineup the sprockets properly and reinstall the conveyor. | 2 | Robert
17010456 | 2017-03-30 |  | Line 2 Cooler Discharge Conveyor L2CD_2S1 | Remove belt for cleaning | 2 | Robert
17010567 | 2017-03-31 | 2 | Bread Basket Loader L2PF2 | Record parameters for VFD's. See Shawn for sheet and details. Pick up the sheet needing to be filled out from the trays outside D. Powell's office and place the completed sheet in the same place. | 2 | Robert
17011581 | 2017-04-08 | 2 | BREAD LINE 2 BASKET | Record all parameters of the basket loader VFD's into the provided sheets. | 2 | Robert
17011582 | 2017-04-08 | 2 | BREAD LINE 1 BASKET | Record all 160 VFD parameters that are in the basket loaders on L1 with the sheet provided and give to Shawn. | 2 | Robert
17012366 | 2017-04-11 | S | Bread Bagger L1B3 | L1B3- need to replace the drive motor/ brake went bad brake is manually off now replace with new SEW motor AMFBAGR056 in lean room Delmar needs to reroute electrical hard conduit from panel | 2 | Robert
17012706 | 2017-04-14 | 2 | Bread Bagger L2B1 | L2B1- check conveyor overload prox adjust chain and reinstall prox | 2 | Robert
17012898 | 2017-04-17 | 2 | Bread Depanner L1DEP | Check idle rollers to make sure they are functioning. Clean and replace if necessary | 2 | Robert
17013000 | 2017-04-18 | 2 | Bread Dough Chunker L2DCHK | Replace light stack at L2Chunker. Was repaired with tape. | 2 | Robert
17013615 | 2017-04-24 | 1 | Bread Basket Loader L1PF1 | Replace PLC battery, can be done while running. Do not shutdown panel with Battery out or you will loose program. Also, see attached sheet for procedure and make sure to put date on stickers. *****Battery is in the line 1 staging cage in wrapping.***** | 2 | Robert
17013617 | 2017-04-24 | 1 | Bread Basket Loader L1PF3 | Replace PLC battery, can be done while running. Do not shutdown panel with Battery out or you will loose program. Also, see attached sheet for procedure and make sure to put date on stickers. | 2 | Robert
17013618 | 2017-04-24 | 1 | Bread Basket Feed Conveyors Slide L1TF4 | Replace PLC battery, can be done while running. Do not shutdown panel with Battery out or you will loose program. Also, see attached sheet for procedure and make sure to put date on stickers. | 2 | Robert
17013619 | 2017-04-24 | 1 | Bread Basket Loader L2PF1 | Replace PLC battery, can be done while running. Do not shutdown panel with Battery out or you will loose program. Also, see attached sheet for procedure and make sure to put date on stickers. | 2 | Robert
17013620 | 2017-04-24 | 1 | Bread Basket Loader L2PF2 | Replace PLC battery, can be done while running. Do not shutdown panel with Battery out or you will loose program. Also, see attached sheet for procedure and make sure to put date on stickers. This PLC is newer and may need a BA@ battery. See Shawn if this is the case. | 2 | Robert
17013621 | 2017-04-24 | 1 | Bread Basket Loader L2PF3 | Replace PLC battery, can be done while running. Do not shutdown panel with Battery out or you will loose program. Also, see attached sheet for procedure and make sure to put date on stickers. | 2 | Robert
17013622 | 2017-04-24 | 1 | Bread Basket Loader L2PF4 | Replace PLC battery, can be done while running. Do not shutdown panel with Battery out or you will loose program. Also, see attached sheet for procedure and make sure to put date on stickers. | 2 | Robert
17013689 | 2017-04-25 |  | Bread Overwrapper L2W1 | Replace PLC battery and make sure to put date on sticker. See attached procedure. | 2 | Robert
17013690 | 2017-04-25 | 2 | Bread Overwrapper L2W2 | Replace PLC battery and make sure to put date on sticker. See attached procedure. | 2 | Robert
17013691 | 2017-04-25 | 2 | Bread Overwrapper L2W3 | Replace PLC battery and make sure to put date on sticker. See attached procedure. | 2 | Robert
17013692 | 2017-04-25 | 2 | Bread Overwrapper L2W4 | Replace PLC battery and make sure to put date on sticker. See attached procedure. | 2 | Robert
17013715 | 2017-04-25 | 1 | Bread Pan Stacker L1PS | Replace shaft and bearings on the Cross Belt Drive Track. | 2 | Robert
17013721 | 2017-04-25 | 1 | Bread Pan Unstacker L1PUS | Level the Plunger for the Unstacker | 2 | Robert
17013848 | 2017-04-26 | 2 | BREAD LINE 1 TOPPING AND SPLITTING EQUIPMENT | Clean air filter and fan for electrical panel. | 2 | Robert
17013883 | 2017-04-26 | 1 | Bread Splitter / Applicator L2D | Install estop guard L2 seeder. NOTE: There are E Stop guards in one of the EM staging cages. | 2 | Robert
17015021 | 2017-05-03 | 2 | Line 2 Pan Feed Conveyor L2PF_R36 | Please replace the broken pieces of the conveyor. | 2 | Robert
17015022 | 2017-05-03 | 2 | Line 2 Pan Feed (Switching) Conveyor L2PF_R35S | Replace the ripped belt. | 2 | Robert
17015034 | 2017-05-03 | 2 | Line 2 Pan Return (Reject) Conveyor L2PR_R5 | Replace broken links in conveyor belt. | 2 | Robert
17015078 | 2017-05-03 | 1 | Bread Splitter / Applicator L1WS | MPA Flap failed causing the topper to alarm | 2 | Robert
17015816 | 2017-05-07 |  | Bread Basket Loader L1PF3 | New o-ring (wheels) needed for line one pattern former. No traction on bread. Please return to Rudy. | 2 | Robert
17015869 | 2017-05-08 |  | Bread Basket Loader L1PF4 | All of the O-Ring rollers need to be replaced. They line st their elasticity. Not consistent at all | 2 | Robert
17016013 | 2017-05-10 | 2 | Bread Pan Stacker Feed Conveyor L1PS2 | Replace broken pieces of tabletop conveyor. Cut back wear strip on oven side drive side sprocket. It's rubbing against sprocket | 2 | Robert
17016080 | 2017-05-10 | 1 | Line 2 Cooler Feed Conveyor L2C3 | Remove conveyor belt and deliver to wash room for cleaning and sanitation deep cleaning of conveyor frame. | 2 | Robert
17016081 | 2017-05-10 | 1 | Line 2 Cooler Feed Conveyor L2C3 | Install conveyor belt once belt and conveyor cleaning is complete. | 2 | Robert
17016083 | 2017-05-10 | 1 | Line 2 Cooler Feed Conveyor L2C4 | Remove conveyor belt and deliver to wash room for cleaning and Sanitation deep cleaning of conveyor frame. | 2 | Robert
17016084 | 2017-05-10 | 1 | Line 2 Cooler Feed Conveyor L2C4 | Install conveyor belt after belt and frame have been cleaned. | 2 | Robert
17016086 | 2017-05-10 | 1 | Line 2 Cooler Feed Conveyor L2C5 | Remove conveyor belt and deliver to wash room for cleaning and Sanitation deep cleaning of conveyor frame. | 2 | Robert
17016087 | 2017-05-10 | 1 | Line 2 Cooler Feed Conveyor L2C5 | Install conveyor belt after belt and frame cleaning is complete. | 2 | Robert
17017067 | 2017-05-11 | 2 | Bread Proofbox L1PB | The humidity display is not showing the actual humidity, it needs to be adjusted to ensure the accuracy of the humidity. | 2 | Robert
17017079 | 2017-05-11 | 2 | BREAD LINE 1 TOPPING AND SPLITTING EQUIPMENT | Repair the plate to collect the topping under the topping machine. | 2 | Robert
17017081 | 2017-05-11 |  | BREAD LINE 1 TOPPING AND SPLITTING EQUIPMENT | Equipment overloading topping constantly | 2 | Robert
17017115 | 2017-05-12 |  | Bread Packing Conveyor L2SW3 | L2SW3 repair 2nd white roller drive gear, inspect balance while apart | 2 | Robert
17017120 | 2017-05-12 |  | Bread Bagger Feed Conveyor L2BF2A | L2BF2A need to flex and modify catch pan by adding hinges one side and clamp other side | 2 | Robert
17017152 | 2017-05-12 |  | Bread Dough Divider - L2DIV | Replace cutting head assembly bearings and pivot shafts bearings | 2 | Robert
17017153 | 2017-05-12 |  | BREAD LINE 1 MAKE UP DOUGH DIVIDER | Replace cutting pivot shafts bearings and seals | 2 | Robert
17017164 | 2017-05-12 | 1 | Bread Proofbox L1PB | Check the humidity system of the Proofer also check the radiator and steam valve for any leaks throughout the system. | 2 | Robert
17017179 | 2017-05-12 | 2 | BREAD LINE MAKE-UP CONVEYORS | Constant pan jams on pans diverter L1, before molding. | 2 | Robert
17017183 | 2017-05-12 |  | BREAD LINE MAKE-UP CONVEYORS | Exterior indexer sent sideway pan causing mayor pan jam before the proof box. You can see on video 5/12/17 at 14:27hr. It is a recurring problem that affect quality product, operational lost time, waste and increase the risk of an accident for our divider/oven operator. | 2 | Robert
17017278 | 2017-05-13 | 2 | Bread Molder - L1MolderA | Replace drive shaft. Check bearings and gear box. Motor is wobbly. DO NOT DO THIS WORK AT THIS TIME. VERIFY THAT THE SHAFT MATERIAL IS AVAILABLE. DETERMINE WHAT BEARINGS AND/OR BUSHINGS WILL BE NEEDED. GET GEARBOX INFORMATION. GIVE ALL OF THIS INFORMATION TO THE MAINTENANCE PLANNER SO THAT THE PARTS CAN BE LOCATED AND/OR ORDERED AND PROPERLY KITTED. | 2 | Robert
17017339 | 2017-05-13 | 2 | Bread Proofer Infeed Conveyors L1P04A | Install guarding around new type of sensors that were install on the pan injectors. **Guarding is in the line 1 staging cage** | 2 | Robert
17017369 | 2017-05-13 | S | Bread Splitter / Applicator L1WS | Safety labels damaged, it need be changed | 2 | Robert
17017497 | 2017-05-15 | 2 | Bread Bagger L1B4 | Either repair or replace weldment block. | 2 | Robert
17017505 | 2017-05-15 | 2 | Bread Bagger L1B1 | L1B1- need to replace the control crank for the bearing and two for the shaft ( AMF#370-0501-00B) need one of these and( AMF# 370-0826-00B) need two of these for job | 2 | Robert
17017506 | 2017-05-15 | 2 | Bread Bagger L1B1 | L1B1- need to replace the bearings or the drive crank flat(AMF#370-0653-00B) book shows flat # but not bearings | 2 | Robert
17017545 | 2017-05-16 | 3 | Line 2 Pan Feed Conveyor L2PF_R30 | Replace broken pieces of Intralox conveyor belt. | 2 | Robert
17017639 | 2017-05-17 | 2 | Bread Overwrapper L1W1 | overhead chain sprocket being held in position with tie wrap | 2 | Robert
17017641 | 2017-05-17 | 2 | Line 2 Cooler Discharge Conveyor L2CD_2S16 (Running PM) | check belt and hold downs lifted up during break down | 2 | Robert
17017645 | 2017-05-17 | 2 | Line 2 Pan Feed (Switching) Conveyor L2PF_R35S | belts not tracking even with new belts needs to be looked at, may want to get contactor back in on this issue | 2 | Robert
17017718 | 2017-05-17 | S | BREAD LINES 1 AND 2 INGREDIENTS SYSTEMS EQUIPMENT | Shock for dump station is bad | 2 | Robert
17017719 | 2017-05-17 | 2 | BREAD LINE 1 BASKET FEED | Perform an inspection of the entire line tray feed sweepers. Look for any abnormal conditions. Lubricate any points as needed. Write work orders for any abnormal condition found. | 2 | Robert
17017793 | 2017-05-18 | 2 | Bread Twin Pack Bagger L2TPB1 | tucker table assembly is playing and effect on packing | 2 | Robert
17017794 | 2017-05-18 | 1 | BREAD LINE 2 MIXING AREA EQUIPMENT | We are getting a lot of flour build up on top of mixers 10+11. Please repair. SPEND TIME AT MIXERS WHILE RUNNING AND DETERMINE THE SOURCE OF THE FLOUR. ADJUST WHAT CAN. WRITE WORK ORDERS FOR ANY CONDITIONS THAT NEED TO BE REPAIRED ON DOWN DAYS. | 2 | Robert
17017799 | 2017-05-18 | 2 | BREAD LINE 2 | L2 wrapping repair buzzer for change overs see photo for location | 2 | Robert
17018177 | 2017-05-18 | 1 | Bread Basket Feed Conveyors L1ETC07 | L1ETC7 motor has excessive vibration inspect to see weather its the coupling or motor bearings. Repair/ replace as needed. | 2 | Robert
17018206 | 2017-05-19 | 2 | Bread Basket Feed Conveyors L2ETC11 | L2ETC11 check and repair noises tray stop | 2 | Robert
17018245 | 2017-05-19 | 2 | Bread Basket Loader L2PF2 | L2PF2- the flat top Allen screws that mount turn table to stem of shaft are worn through turn table need to repair | 2 | Robert
17018368 | 2017-05-20 | 1 | Bread Oven Feed Conveyor L1OF01 | Pans are turning because of bad transfer onto conveyors. | 2 | Robert
17018550 | 2017-05-22 | S | Bread Validator L1VAL4 | E-STOP doesn't stop the equipment. It keeps on running even when it is pushed down. | 2 | Robert
17018551 | 2017-05-22 | 2 | Bread Full Basket Conveyors L1TC12 | L1- FB12 Drive Unit is spilling fluid heavily on the floor. | 2 | Robert
17018586 | 2017-05-23 | 2 | BREAD LINE 1 PAN RETURN CONVEYORS | Shorten Intralox conveyor on L1PR11 | 2 | Robert
17018587 | 2017-05-23 | 2 | Bread Slicer L2S2 | L2S2- the top removable support arm needs to be repaired or replaced someone beat it with a hammer making it to tight to move when changing blades | 2 | Robert
17018591 | 2017-05-23 | 2 | BREAD LINE 1 MAKE UP DOUGH FLOUR SYSTEMS EQUIPMENT | Dusting flour system creating a cloud of flour (Dust cloud) some times, when we are running. *****Talk to Ignacio and Peter to determine the source of this flour dust "cloud" and validate. Write a new work order based on your findings. | 2 | Robert
17018604 | 2017-05-23 | 2 | Bread Molder - L2MolderB | Check motor and shaft for pressure board. It's starting to dance. Assign to Jon Ritchie | 2 | Robert
17018615 | 2017-05-23 | 2 | Bread Molder - L1MolderA | Both moulder are seeing more single doubles these are not picked up with a alarm | 2 | Robert
17018629 | 2017-05-23 | 2 | Line 1 Bread Bagger Feed Conveyor L1SC2 | *****MOTOR/GEARBOX IN LINE 1 STAGING CAGE***** (OLD MAINTSMART WORK ORDER 506431). Remove motor inspect gear box (oil level) if bad replace as needed. Reinstall motor gear box and test, change inverter settings for decelaration to 0.3 from 0.7 | 2 | Robert
17018735 | 2017-05-24 | 2 | Bread Basket Denester L2DENSTR | L2 denester turn assembly needs repair down day bolts that hold in place worn | 2 | Robert
17018738 | 2017-05-24 | 1 | Bread Oven Loader L1OL | Slot base for a take-up and also level the gear box for L1OvenLoader table top conveyor. Right now the gear box is not level and the chain is vibrating. THIS IS A PRIORITY FOR THE NEXT DOWN DAY. | 2 | Robert
17018767 | 2017-05-24 | 1 | Bread Oven Loader L1OL | loader and feed conveyor there is something wrong as the feed conveyor continues to run if the loader is jammed. Maintenance asked us to stop the oven feed conveyor on the control panel Please identify & correct this issue | 2 | Robert
17018768 | 2017-05-24 | 2 | Bread Liquid Scaling Tank Line 1 L015 | The NEW RAISIN Juice scaling system is leaking from discharge pump | 2 | Robert
17018826 | 2017-05-25 | 2 | Line 2 Bread Wrapping Feed (Lane 2 Switching) Conveyor L2WF_S22 | L2WF-S22 replace missing out feed transfer roller | 2 | Robert
17018867 | 2017-05-25 | 3 | Bread Dough Chunker L1DCHK | lets look @ location of safe wire as we are seeing alot of estops as the dough hits the wire stopping chunker We all can discuss location of wire to determine where is the best spot | 2 | Robert
17018869 | 2017-05-25 | 2 | Bread Dough Divider L1DIV | Please look @ the CIP process when the CIP is completed everything is still dirty & the chambers are fill with dough I am not sure this process is working correctly . Maintenance is doing alot of manual work after the system has been CIPed | 2 | Robert
17018870 | 2017-05-25 | 2 | Bread Molder - L1MolderA | when the line stops the Aside is jamming up with dough Patrick explained this to Joe Please correct issues | 2 | Robert
17018893 | 2017-05-25 | 2 | Bread Wrapping Feed Conveyor L2WF06 | Conveyor very dirty needs washing | 2 | Robert
17018894 | 2017-05-25 | 2 | Bread Wrapping Feed Conveyor L2WF07 | Conveyor very dirty needs washing | 2 | Robert
17018895 | 2017-05-25 | 2 | Bread Wrapping Feed Conveyor L2WF08 | Conveyor very dirty needs washing | 2 | Robert
17018980 | 2017-05-26 | 2 | Bread Packing Conveyor L2PFF2B | L2PFF2B conveyor is some time jumping and hesitant | 2 | Robert
17019046 | 2017-05-26 | 2 | Bread Basket Feed Conveyors L2ETC10 | L2ETC10 tray stop cylinder hardware shot, needs to be repaired/ replaced. | 2 | Robert
17019054 | 2017-05-26 | 2 | Bread Basket Loader L2PF4 | Cut off the marked area of the guide so it can come inside of the stop plate for proper adjustment | 2 | Robert
17019084 | 2017-05-27 | 2 | Bread Bagger Feed Conveyor L2BF2B | L2BF2B repair or replace tensioner so the wire can be removed | 2 | Robert
17019110 | 2017-05-27 | S | Bread Pan Return Conveyor L1PR17 | Replace or repair connection cable to the disconnect switch on L1PR17 the cable have exposes wires | 2 | Robert
17019123 | 2017-05-27 | 1 | Bread Dough Mixer M10MIX | Check chain, motor, brake and other repairs completed last week to ensure that the repairs are holding and there is no other reason for the failure to have occurred. | 2 | Robert
17019124 | 2017-05-27 | 1 | Bread Dough Mixer M11MIX | Check mixer chain, motor, brake and any other components that could be affected as mixer 10 was. Ensure there is no condition that could cause this mixer to fail as the other mixer did. | 2 | Robert
17019135 | 2017-05-27 |  | Bread Basket Denester L2DENSTR | Repair or replace opr side door handle comes loose during operation | 2 | Robert
17019158 | 2017-05-28 | 3 | Bread Overwrapper L2W2 | L2W2 drive chain needs to remove and clean | 2 | Robert
17019208 | 2017-05-28 | 2 | LINE 2 MAKE-UP AREA EQUIPMENT | Flour reclaim the blue belt inside oven side is ripped | 2 | Robert
17019212 | 2017-05-28 | 1 | Line 2 Pan Feed Conveyor L2PF_R35B | R35 belt broke we had none in stock running 1 side with no belt | 2 | Robert
17019215 | 2017-05-28 | 2 | Bread Dough Mixer M01MIX | Liquid sponge discharge pump behind the mixers is still leaking please repair | 2 | Robert
17019224 | 2017-05-28 | 2 | Bread Full Basket Conveyors L1TC08 | L1TC8- the incline motor has a wobble while running may be bent shaft needs to be inspected | 2 | Robert
17019225 | 2017-05-28 | 2 | Bread Bagger L2B4 | L2B4- check bag tables and air jets production complaint of loosing bags | 2 | Robert
17019226 | 2017-05-28 | 2 | Bread Bagger L2B2 | L2B2- check bag tables and air jets production complaint of loosing bags | 2 | Robert
17019233 | 2017-05-28 |  | Bread Basket Feed Conveyors Slide L1TF3 | Rearrange and label the wires in case we have to perform a troubleshooting in the future. | 2 | Robert
17019305 | 2017-05-30 | 2 | Bread Basket Loader L1PF2 | Replace all roller bed o-rings. | 2 | Robert
17019306 | 2017-05-30 | 2 | Bread Basket Loader L1PF1 | Change all roller bed o-rings. | 2 | Robert
17019311 | 2017-05-30 |  | BREAD LINE 1 MIXERS | Rope holding pipes between mixers. | 2 | Robert
17019312 | 2017-05-30 |  | BREAD LINE 2 DOUGH | Mixing line 2- The table to place the gluten closer to the dump station has not food grade condition. | 2 | Robert
17019313 | 2017-05-30 |  | BREAD LINE 1 OVEN RELATED EQUIPMENT | Oven unloader - Sensor not reading continuously, stopping the oven (2 - 6 min over bake) causing waste and consumer complaints due to burnt product. | 2 | Robert
17019318 | 2017-05-30 | 2 | Bread Overwrapper Bypass Conveyor L2WB2 | Repair or Replace the broken guide. | 2 | Robert
17019381 | 2017-05-31 | 2 | Line 2 Pan Feed Conveyor L2PF_R36 | Change out broken pieces on L2PR36. Picture is of the belt up in the lean room. | 2 | Robert
0 | 2017-01-01 | T | Time Off | Lunch Time | 1 | Robert
1 | 2017-01-01 | T | Time Off | Break Time | 1 | Robert
10 | 2017-01-02 | O | Other Tasks | Union Business | 1 | Robert